## Queries
Cisco Queries: Services and Interaction
Sr No. | Query Subject | Query Details | Status | Complexity | Comments | Owner
Dashboard - Mailroom
1 | Initial Popup: Comply with Cisco Shipping Policy | Initial popup that comes with this page, should it be based on local storage or service based. If we use local storage based check then this will consume 1 less service but this pop up will appear for the user again if the browser cache and cookies are cleared. Where as if this popup is a service based we would need maintenance of the flag for this service but will not appear once the user has accepted the terms and conditions | Open | Easy |  | Rakesh
2 | Initial Popup: Comply with Cisco Shipping Policy | Will the text of terms and conditions be static or will it be service based | Open | Easy |  | Rakesh
3 | Username: Interactivity on triangle near username | What is the Interactivity on the triangle near the username? What options does the user get? | Open | Easy |  | Bala
4 | Shipments Tile: Services | Require detials about the services which fetch the data for the mentioned tile. Details are needed along with JSON format of data coming in. | Open | Medium | Data should be coming in consolidated format of day and week | Rakesh
5 | Track your Shipment Tile: Services | Require detials about the services which fetch the data for the mentioned tile. Details are needed along with JSON format of data coming in. We also need all the possible states that will be coming as a response so that we can configure our tiles accordingly. Currently it is just showing In Transit. | Open | Medium |  | Rakesh
6 | My Shipment: Services and Interaction | Is there any interaction apart from sorting on the My Shipment Tile. Require detials about the services which fetch the data for the mentioned tile. Details are needed along with JSON format of data coming in. | Open | Medium |  | Rakesh
7 | Notifications Tile: Services and Interaction | What is the action that should take place when the user clicks on the notifications. For example if we consider staying in the dashboard app: User can be navigated from one of the 5 main pages or states of the applications based on the data available with the notification or he can be taken to the miscelanious page which is yet to be designed. Require detials about the services which fetch the data for the mentioned tile. Details are needed along with JSON format of data coming in. | Open | Medium |  | Rakesh
8 | Notifications Tile: View All Notifications action | It is preferred to consume 1 single service for all the notifications. Action on View All Notifications: Takes to the miscellaneous page. Designs for the page are not avaialble yet. | Open | Hard |  | Bala
9 | Bulk Upload Tile: Servies and Interaction | Are the serivces for upload file in place. Is there any design available for upload progress to be shown or states through whith the tile will go through | Open | Hard |  | Bala/Rakesh
10 | Training/Updates: Services and Interaction | This tile shows all the videos of training which is mandatory and needs to be completed. As per the discussion the video player would come up as a pop up. Is there a design available for the same or shall we assume and go ahead with our own pop over. Require detials about the services which fetch the data for the mentioned tile. Details are needed along with JSON format of data coming in. | Open | Medium |  | Bala/Rakesh
11 | Click to Chat: Services and Interaction | As of now, we don’t have the details of how the Chat Box will look like once it is open. Is the interaction designed? Are the chat services available? It was discussed that chat services is not there for Drop 1 and Drop 2. Is it planned to be integrated? | Open | Hard |  | Bala/Rakesh
Request Shipment: Shipping Details Module
12 | Shipping Policy Checklist: Interaction | Is the shipping policy checklist a static or dynamic content. Wireframes do not have any interaction over it. Please provide what is the interaction result over the link. | Open | Easy |  | Bala
13 | Shipping Policy: Select Profile | Interaction on selection of different profiles is not available. Also the details of the services in which the number of profiles would be avaialble. | Open | Easy |  | Rakesh
14 | Shipping Policy: Edit/Save/Create Profile Services | Services for Edit, save or creation of profile are not in place for sender and receiver. | Open | Medium |  | Rakesh
15 | Charge To: Interaction | Services for getting the department code is not avaialbe. | Open | Easy |  | Rakesh
16 | Request Shipment: Save the data while switching between tabs | We will use local storage to save the data while the user switches between the tabs rather than consuming a service. Please confirm if that is fine. | Open | Easy |  | Rakesh
17 | Package Details: Upload Service and Interaction | Is there any upload service avaialbe for Package details bulk upload. Is there any interaction to show the progress or cancellation feature of upload. | Open | Medium |  | Rakesh/Bala
18 | Package Details: Add a package | Is there a service to save the package details? Would there be a submit button to save the data? | Open | Medium |  | Rakesh/Bala
19 | Preview and Print: Interaction on Edit | Interaction on edit is not mentioned. Please let us know the consumed services too. | Open | Easy |  | Rakesh/Bala
20 | QR Code: Whats the use of QR code on mobile and tablet? | Query - Usability | Open | Easy |  | Rakesh/Bala
21 | Submit for Compliance Services | Is there any services available for submit for compliance? Post that which page the user should land on or what pop over should come or any success/failure message? | Open | Medium |  | Rakesh/Bala
Track Shipment
22 | Track Shipment: Services for data | Are the services avaialble for track shipment data to be fetched and displayed? | Open | Medium |  | Rakesh
23 | Success Failure Pop-over Messages | Please list down all the success failure states in the interaction and also how they will be displayed. | Open | Medium |  | Rakesh/Bala
24 | Shipment: Detailed Data Loading | Loading of the details of the shipment would be done on click or on the initial loading of the page? Interaction and details on the edit icon are not provided. | Open | Medium |  | Rakesh/Bala
25 | Pagination Data | Would the pagination data be loaded based on request or would it be loaded in one go. | Open | Hard |  | Rakesh/Bala

## Assumptions
Key Assumptions
Sr No. | Assumption | Comments
1 | Drop 1: Services integration is not required.
2 | Functional Requirements: Logic of the dashboard app is to be documented and based on which the estimations will be impacted.
3 | Services: Necessary services would be in place by drop 2 along with detailed description and documentation. If the services are not it place the pages would be delivered only using sample JSON data.
4 | Is this 940px width page in scope or is it locked down by client?