## UX Team
UX Team (Gaurav Lal's team) | [5 empty] | Planned |  | Actual |  | Estimated hours | [5 empty] | Actual
Role | Identified resource | Planned LCR | Actual LCR | Planned Cost | Actual Cost to date | Start date | End date | Start date | End date | 2014-10-31 | 2014-11-15 | 2014-11-30 | 2014-12-15 | 2014-12-31 | Total Cost | 2014-10-31 | 2014-11-15 | 2014-11-30 | 2014-12-15 | 2014-12-31 | Jan'15 | 2015-02-15 | Total Cost | Total hours charged | Forecasted hours | Remaining hours | Cost
UX Strategist | gaurav.lal | 36.8732 | 36.436 | 2522.124 | 437.232 | 2014-10-20 | 2014-10-29 |  |  | 68 | - | - | - | - | 2522.124 |  |  | 6 |  |  | 6 |  | 437.232 | 12 | 68 | 56 | 2040.4159
Creative Lead | s.babu.thotakuri | 26.461 | 18.47 | 1809.9303 | 166.23 | 2014-10-20 | 2014-10-29 |  |  | 68 | - | - | - | - | 1809.9303 | [5 empty] | 9 |  | 166.23 | 9 | 68 | 59 | 1089.73
IA 1 | madhuri.krishna | 20.9731 | 13.3863 | 7710.7555 | 4457.6472 | 2014-10-20 | 2014-12-17 |  |  | 86 | 86 | 86 | 94 | 17 | 7710.7555 |  |  | 153 | 27 |  | 135 | 18 | 4457.6472 | 315 | 369 | 54 | 722.8617
IA 2 | bala.x.sundaram | 10.6448 | 14.0891 | 910.1301 | 5818.8161 | 2014-10-20 | 2014-10-31 |  |  | 86 | - | - | - | - | 910.1301 |  |  | 153 | 27 |  | 143 | 90 | 5818.8161 | 323 | 86 | -237 | -3339.1269
Visual Designer 1 | v.shankaranarayanayy | 20.9731 | 16.6632 | 5738.2366 | 4682.3654 | 2014-10-20 | 2014-12-02 |  |  | 86 | 86 | 86 | 17 | - | 5738.2366 |  |  | 18 | 27 |  | 146 | 90 | 4682.3654 | 191 | 275 | 84 | 1399.7106
Visual Designer 2 | bharath.kumar.r | 10.6448 | 13.14 | 1365.1952 | 3416.4 | 2014-10-20 | 2014-11-07 |  |  | 86 | 43 | - | - | - | 1365.1952 |  |  |  | 76 |  | 139 | 45 | 3416.4 | 215 | 129 | -86 | -1130.04
|  |  |  | 20056.3717 | 18978.6906 | [9 empty] | 20056.3717 | [7 empty] | 18978.6906 | 1065 | 995 | -70 | 783.5514
Additional work

## FED team
FED Team (Danashree's team) | [5 empty] | Planned |  | Actual |  | Estimated hours | [6 empty] | Actual
Role | Identified resource | Planned LCR | Actual LCR | Planned Cost | Actual Cost to date | Start date | End date | Start date | End date | 2015-01-15 | 2015-01-31 | 2015-02-15 | 2015-02-28 | 2015-03-15 | 2015-03-31 | Total Cost | 2015-01-15 | 2015-01-31 | 2015-02-15 | 2015-02-28 | 2015-03-15 | 2015-03-31 | 2015-04-15 | Total Cost | Total hours charged | Forecasted hours | Remaining hours | Cost
FED SSE | sunny | 10.6448 |  | 3053.7573 | 0 | 2015-01-15 | 2015-03-20 |  |  | 5.814 | 63.954 | 58.14 | 58.14 | 58.14 | 29.07 | 3053.7573 | [7 empty] | 0 | 0 | 244.188 | 244.188 | 0
FED TL | ankit | 20.9731 |  | 6016.7158 | 0 | 2015-01-15 | 2015-03-20 |  |  | 5.814 | 63.954 | 58.14 | 58.14 | 58.14 | 29.07 | 6016.7158 | [7 empty] | 0 | 0 | 244.188 | 244.188 | 0
[5 empty] | 0 | [19 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | [19 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | [19 empty] | 0 | 0 | 0 | 0
[5 empty] | 0 | [19 empty] | 0 | 0 | 0 | 0
|  |  |  | 9070.4731 | 0 | [10 empty] | 9070.4731 | [7 empty] | 0