## Project Details
CISCO: User Experience Estimates
Cross Channel Experience
Deliverables & Milestones
Project Deliverables | Deadline Date | Status
Project Plan | 2014-10-20 | Completed
Stakeholder Interview Report | 2014-10-27 | Completed
High level IA | 2014-10-28 | Completed
task Flows | 2014-10-30 | Completed
Concept Designs | 2014-11-20 | Partially Completed
High Level Design Documentation | 2015-01-19
Detailed Designs | 2015-01-29
UI Documentation | 2015-02-10
Total Effort Days | 115

## Project Plan
Project Plan
|  | STAFF |  |  |  | Locked Cells |  | Start Month: | 2014-09-22 | [8 empty] | Sep | [5 empty] | Oct | [20 empty] | OCT | [9 empty] | Nov | [29 empty] | Dec | [30 empty] | Jan | [30 empty] | Feb | [27 empty] | Mar | [30 empty] | Apr
Activities | Completion | UX Architect TL | UX Architect SSE | Visual Designer TL | Visual Designer SSE |  | Activity Completion ($) | Effort Days | Start | End | Completion Status | Comments | Deliverables | Dependencies | time axis 2014-09-22 to 2015-04-22
 | time axis 2014-09-22 to 2015-04-22
Activity 1: Cross Channel Design Strategy | [5 empty] | activity completion list |  |  | 2014-10-20 | 2015-01-19
Project plan and setup | 100% | 1 | 1 |  |  | 0% | #REF! | 1 | 2014-10-20 | 2014-10-20 | Completed |  | Project Plan
Stakeholder Interviews (4- 5) with some end users as well Understand High Level Requirements / Features | 100% | 2 | 1 |  |  | 25% | #REF! | 2 | 2014-10-21 | 2014-10-27 | Completed | Sessions conducted and the findings have been discussed with the client |  | The client to set up meetings with the stakeholders to understand users, key tasks, and high level requirements of the application | 2014-10-22: Diwali holidays
Define high level Information Architecture | 100% | 1 | 1 |  |  | 50% | #REF! | 1 | 2014-10-28 | 2014-10-28 | Completed | High level IA has been created and shared with the client. | High level IA
Create Storyboards for the key task - Request for Shipment | 100% | 2 | 2 |  |  | 75% | #REF! | 2 | 2014-10-29 | 2014-10-30 | Completed | Storyboard and taskflow has been created and shared with the client. Client has agreed upon the task flows created. | Task flows with interactions
Create design concept for 1 key task (2 - 4) wireframes for Mobile, Tablet and website | 100% | 5 | 5 |  |  | 100% | #REF! | 9 | 2014-10-31 | 2014-11-12 | Completed | Wireframes have been created for dashboard and create shipment flow, have discussed this with the cliet and wireframes have been refined. | Conceptual designs illustrating the concepts for the key pages | Client to provide brand styleguide
Create design concept for 1 homepage visually treated screens (as per the branding) For Mobile, Tablet and website | 50% |  |  | 3 | 3 |  |  | 6 | 2014-11-13 | 2014-11-20 | Partially Completed | 3 visual design options have been created as per the two different guidelies shared by client. Need confirmation on which theme needs to be followed for the creative design team to create rest of visual designs | Conceptual visual designs (distinct design options)
Create visual design concept for 3 wireframes (as per the branding) For Mobile, Tablet and website |  |  |  | 2 | 2 |  |  | 4 | 2015-01-05 | 2015-01-08
Share the concept with the client and get feedback from the end users | 50% | 1 | 1 | 1 | 1 |  |  | 3 | 2015-01-08 | 2015-01-12 | Partially Completed | Wireframes were shared with the client and has bee refined based on their feedback. Need them to choose the visual design option for creative team to work on it further. |  | The client to provide signoff on the concept designs
Iterate Design | 50% | 2 | 2 | 1 | 1 |  |  | 2 | 2014-12-02 | 2014-12-03 | Partially Completed
Iterate Design - Client feedback |  | 3 | 3 | 3 | 3 |  |  | 3 | 2015-01-12 | 2015-01-14
Define branding across all channels | 0% |  |  | 3 | 3 |  |  | 3 | 2015-01-13 | 2015-01-15 | Yet to start |  | High Level Design Documentation | High Level Design Documentation
Handover to FED team for creating HTMLs | 0% |  |  | 1 | 1 |  |  | 1 | 2015-01-19 | 2015-01-19
Days for activity |  | 17 | 16 | 14 | 14
Activity 2: Detailed Design (Wireframes and Visual Design) | [8 empty] | 2015-01-13 | 2015-01-29
Define detailed IA (per channel) | 0% | 2 | 2 |  |  |  | #REF! | 2 | 2015-01-13 | 2015-01-14 | Yet to start |  | Detailed IA | Client to provide signoff
Detailed Design for Web - Track, edit/ cancel, support and master setup Wireframe | 0% | 4 | 4 |  |  |  | #REF! | 4 | 2015-01-15 | 2015-01-20 | Yet to start |  | Detailed page level wireframes | Client to provide signoff
Detailed Design for Web - Track, edit/ cancel, support and master setup Visual Design | 0% |  |  | 2 | 2 |  |  | 3 | 2015-01-20 | 2015-01-22 | Yet to start |  | Visually treated screens | Client to provide signoff
Detailed Design for Tablet - Track, edit/ cancel, support Wireframe | 0% | 3 |  |  |  |  | #REF! | 3 | 2015-01-21 | 2015-01-23 | Yet to start |  | Detailed page level wireframes | Client to provide signoff
Detailed Design for Tablet - Track, edit/ cancel, support Visual Design | 0% |  |  | 3 |  |  |  | 3 | 2015-01-23 | 2015-01-29 | Yet to start |  | Visually treated screens | Client to provide signoff
Detailed Design for Mobile - Track, edit/ cancel, support Wireframe | 0% |  | 3 |  |  |  | #REF! | 3 | 2015-01-21 | 2015-01-29 | Yet to start |  | Detailed page level wireframes | Client to provide signoff
Detailed Design for Mobile - Track, edit/ cancel, support Visual design | 0% |  |  |  | 3 |  |  | 3 | 2015-01-23 | 2015-01-29 | Yet to start |  | Visually treated screens | Client to provide signoff
Present the design | 0% | 1 | 1 |  |  |  | #REF! | 3 | 2015-01-25 | 2015-01-29 | Yet to start |  |  | Client to provide signoff
Client feedback and iterate design |  | 3 | 3 | 3 | 3 |  |  | 3 | 2015-01-30 | 2015-02-03
Days for activity |  | 13 | 13 | 8 | 8
Activity 3:UI Specifications Document | [8 empty] | 2015-02-04 | 2015-02-10
Document the design specification per channel | 0% |  |  | 3 | 3 |  | #REF! | 3 | 2015-02-04 | 2015-02-06 |  |  | UI Specifications Documentation - Provide detailed information on the page design, page types, usage of different design/form elements, and colors. The standards will establish "rules" governing the look-and-feel of all pages and elements such as Navigation Metaphors and Placement (Tabs, breadcrumbs, drop-down menus) , Screen Areas (location of header, footer, content area, etc.) , Header Standards, Footer Standards, Error Handling Messages Approach | Client to provide signoff
Handover to FED team for creating HTMLs. VD will Provide development support | 0% |  |  | 3 | 3 |  | #REF! | 3 | 2015-02-07 | 2015-02-10
Days for activity |  |  |  | 6 | 6
Total |  | 30 | 29 | 28 | 28 |  | #REF!
HTML Development Effort
|  | STAFF |  |  |  | Locked Cells |  | Start Month: | 2014-12-10
Activities | Completion | UI Lead TL | UI Dev SSE | UI Dev SE |  |  | Activity Completion ($) | Effort Days | Start | End |  |  | Deliverables | Dependencies
Activity 1 - HTML development from Drop 1
Project plan and Setup | 0% | 2 | 1 | 1 |  |  |  | 2 | 2015-01-15 | 2015-01-16 |  |  | Project plan and setup | bar: 2015-01-15 to 2015-01-16
Handover from UX team | 0% | 1 | 1 | 1 |  |  |  | 1 | 2015-01-19 | 2015-01-19 |  |  | Understanding designs from UX | Wireframes from UX team | bar: 2015-01-19
Analyze and Design | 0% | 3 | 2 |  |  |  |  | 3 | 2015-01-20 | 2015-01-22 |  |  | Design classes and layouts | bar: 2015-01-20 to 2015-01-22
Develop HTML Pages | 0% | 3 | 5 | 10 |  |  |  | 10 | 2015-01-23 | 2015-02-06 |  |  | Build HTML pages | bar: 2015-01-23; 2015-01-27 to 2015-01-30; 2015-02-02 to 2015-02-06
Test HTML Pages | 0% | 2 | 2 | 6 |  |  |  | 6 | 2015-02-09 | 2015-02-16 |  |  | Test HTML Pages | bar: 2015-02-09 to 2015-02-13; 2015-02-16
Days for activity |  | 11 | 11 | 18 | 40
Activity 2 - HTML development from Drop 2
Handover from UX team | 0% | 1 | [5 empty] | 1 | 2015-02-09 | 2015-02-09 |  |  | Understanding designs from UX | Wireframes from UX team | bar: 2015-02-09
Analyze and Design | 0% | 4 | 4 |  |  |  |  | 4 | 2015-02-10 | 2015-02-13 |  |  | Design classes and layouts | bar: 2015-02-10 to 2015-02-13
Develop HTML Pages | 0% | 5 | 7 | 15 |  |  |  | 15 | 2015-02-16 | 2015-03-06 |  |  | Build HTML pages | bar: 2015-02-16 to 2015-02-20; 2015-02-23 to 2015-02-27; 2015-03-02 to 2015-03-06
Test HTML Pages | 0% | 4 | 5 | 10 |  |  |  | 10 | 2015-03-09 | 2015-03-20 |  |  | Test HTML Pages | bar: 2015-03-09 to 2015-03-13; 2015-03-16 to 2015-03-20
Days for activity |  | 14 | 16 | 25 | 55
Oct 22,23&24 - Diwali Holidays
Dec 25 - Christmas Holiday
1 Jan - New Year
26 Jan - Indian Republic Day
`

## Assumptions
S.No | Type | Description | Assigned To | Comments
HTML Development Assumptions
1 | HTML | HTML5, CSS3 and JavaScript / Angular.js have been considered for the solution.
2 | HTML | Laptop/Desktop, tablet, and Mobile are the target channels for the development.
3 | HTML | Assumed that we will be developing content for English languages only
4 | HTML | UI wireframes are not available so estimates are uncertain, once we have wireframe estimate must be revisited.
5 | HTML | Design will be done in responsive manner to support different resolutions and devices
6 | HTML | No sensitive data storage considered
7 | HTML | No encryption/decryption of data
8 | HTML | Project management is out of scope and should be included as part of overall project management
9 | HTML | 12 application pages (2 Simple, 6 Medium, and 4 Complex) have been considered for estimation
10 | HTML | Below are the browsers which have been kept in scope. If any other browser support and downgrade version supports are required extra effort would be needed. a. Chrome latest stable version (Version 32.0.1700.107 m) b. Safari latest stable version (Safari 10.6 + for Mac ) c. IE latest stable versions ( IE 9+) d. Firefox latest stable version (version 27)
11 | HTML | For device specific test, testing will be done on the emulators a. iOS Emulator b. Android Emulator
12 | HTML | Assumed 9 hours a day for IDC.
13 | HTML | Change enablement, Service introduction, Deploy, and Development environment support is out of scope
14 | HTML | 4183 Create Unit Tests - increased this by 10% to take care of testing across 4 browsers and 3 emulators
15 | HTML | 5710 Execute Assembly Test - increased this by 10% to take of testing across 4 browsers and 3 emulators
16 | HTML | 5790 Manage and Perform Fixes - is increased by 10% to take care of issue fixing due to multi-browser and device testing
17 | UX | Stakeholder Reviews: The client will schedule checkpoints with the stakeholders
18 | UX | For datagathering session, client will provide the users
19 | UX | Accenture team will create visual designs for 25 - 30 templates across various channels as stated in the inventory sheet. Only 1 round of iteration at the concept design stage
20 | UX | Cisco will provide brand guidelines and design standards for the visual designs
21 | UX | Project plan factors design for Desktop, iPad and iPhone 4s only. Any increase in number of devices will impact the timelines and effort

## Queries
S. no | Type | Queries | Assigned To | Comments
1 | HTML | which are the devices to be considered for development and testing ?
2 | HTML | If we testing on actual devices who will host the application and who wil bare the server cost ?
3 | UX | What are the break points required for the responsive design. We have factored for just one (iPhone 4s). Any addition will impact the timelines and effort
4 | UX | Need sign off on the inventory. Any change will impact the timeliness and effort.
5 | UX | When will the brand style guide be shared?
6 | UX | What is the minimum resolution of screen that desktop should support.